## Gantt
Phase | Task | Start Week | End Week | Responsible
Proof of Concept | Market study & competitors analysis | 1 | 2 | Product Owner
Proof of Concept | Define functional specifications (Smart Fridge + Drive integration) | 2 | 3 | Product Owner
Prototype | Develop AI prototype (object recognition) | 3 | 5 | AI Engineer
Prototype | Develop mobile app (inventory + Drive sync) | 3 | 5 | Mobile Dev
Prototype | Integrate Drive API (E.Leclerc sandbox) | 5 | 6 | Backend Dev
Industrialisation | Finalize hardware integration (IoT modules) | 7 | 8 | IoT Engineer
Industrialisation | RGPD compliance & data privacy validation | 8 | 9 | Privacy Officer
Communication | Internal communication (team sync, planning updates) | 2 | 4 | PO + All
Communication | External communication (board report + budget request) | 8 | 9 | PO + Business Dev
Soutenance | Final presentation & documentation review | 10 | 10 | All