## Risks
Risk | Probability (Low/Med/High) | Impact (Low/Med/High) | Mitigation Strategy
AI misidentifies products (false detection) | Medium | High | Supervised learning phase + manual correction in app
Dependency on E.Leclerc Drive API | Medium | High | Develop generic multi-retailer integration early
Privacy & RGPD concerns (camera data leak) | High | High | Edge AI processing + clear data policy
Hardware integration failure | Low | Medium | Test phase with modular components before integration
Budget overrun | Medium | Medium | Budget buffer 10% + priority-based features